## Sheet1
Risk ID | Risk Description | Likelyhood (1-5) | Likelihood Justification | Impact (1-5) | Impact Justification | Likelyhood * Impact | Mitigation Technique | Last Changed
Risk001 | iRedMail Is more complicated to set up than thought. | 4 | An investigative attempt to use iRedMail proved it to be at least moderately complicated. | 3 | Spending more time than planed setting up the server will leave less time to work on other important features. | 12 | Allocate more time to set up the email server. | v1.0
Risk002 | Spam filters make the application obsolete. | 2 | Spam and malicious mailing has been ongoing for many years. | 2 | The application would still have the possibility for better privacy, security and contact control. | 4 | Develop and add more innovative features when time allows. | v1.0
Risk003 | Bugs in the System. | 5 | Bugs exist in even the most professionally developed software. | 4 | If a bug prevents a key piece of functionality during the demonstration it could jeopardise the coursework marks. Bugs may also create a bad reputation for the software and therefor damage its successfulness. | 20 | Continuous and vigorous testing needs to be carried out on all aspects of the software. UI tests, integration test, unit tests, etc. will be carried out. | v1.0
Risk004 | Gaps in requirements. | 3 | The requirements have been thoroughly examined, however, it is never possible to plan for every eventuality. | 3 | A change request will need to be issued and the extra work will be needed to implement the new requirements. | 9 | Have peers and mentor review requirements | v1.0
Risk005 | Underestimating work items. | 5 | It is common for programmers to overestimate tasks or their own abilities | 3 | This will have a negative effect on the schedule, possibly resulting in the project not being completed. | 15 | Estimates will be constantly reviewed against actual times and adjusted to match. | v1.0
Risk006 | Extenuating circumstances (illness, family matter, etc.). | 2 | By looking at the number of people in the course and the number of people who have submitted, there is a small but fair chance that an extenuating circumstance could occur. | 3 | The impact will depend on the circumstance. However, the impact should be lessened as the university has procedures in place to help in such circumstances. | 6 | Planning to finish work early should enable more time to deal with any external circumstance that occurs. | v1.0
Risk007 | Users will not understand how to use the app. | 2 | The website is well designed with usability take into account. | 5 | If users do not know how to use the application, they will likely quickly move to a more user friendly alternative. | 10 | Usability tests will be carried out and the results will be fed back into the requirements | v1.0
Risk008 | Users will not understand what the app does. | 4 | From discussing the principle idea with peers, the primary concept seems hard to grasp. | 4 | If users do not understand what the application does, more established email services may seem a better choice. | 16 | Usability tests will be carried out and the results will be fed back into the requirements | v1.0
Risk009 | The application takes too long to manage compared to normal email services. | 4 | Generating a new address for every contact could be a hassle. | 4 | Users may change to another email provider if processes take too long. | 16 | A browser extension is planned to automatically create and fill new emails into forms on browsers. | v1.0
Risk010 | The system will be hacked. | 2 | It is unlikely that anybody would want to hack the system unless it had important users. | 5 | If the system was hacked the reputation of the developer and product would be at risk. If incompetence is found this could possibly lead to jail time. | 10 | The software should be penetration tested. | v1.0
[5 empty] | Key | Low Priority
Medium Priority
High Priority